## Slide 1: Maree Michel Bridge GRS-IBS Abutment: Lessons Learned
Jesse G Rauser, PE

## Slide 2: Project Overview

## Slide 3: Project Overview
Project is located along LA Hwy 91 in Vermilion Parish
Consisted of replacement of two timber bridges over Maree Michel Canal
First GRS abutments designed & constructed for LADOTD projects
  Every Day Counts initiative
Designed in-house and let for bidding
Project Location

## Slide 4: Project Site Selection
Rural setting with low ADT
  < 500 vehicles
Relatively short spans
  Creek Bridge: 35 ft
  Maree Michel Bridge: 72 ft
Bridges span irrigation canals with virtually no flow
  Minimal scour concerns
  Very little fluctuation in water elevation
Old Creek Bridge
Old Maree Michel Bridge

## Slide 5: Site Geology
Approx. Site Location
Geological Map of Project Site

## Slide 6: Generalized Soil Profile
Clay Su = 1,740 psf, γ = 125 cf
Sandy Silt φ > 30, γ = 122 cf
Clay Su = 2,100 psf, γ = 117 pcf
Clay Su = 1,500 psf, γ = 118 cf
Clay Su = 820 psf, γ = 122 pcf
Undrained Shear Strength and Unit Weight of Foundation Soil Layers

## Slide 7: Design

## Slide 8: FHWA Implementation Guide
Design commenced with hand calcs closely following the FHWA guide
GRS had to be “sold” to other LADOTD sections (Bridge Design, Project Management)
  Chapters 3 (materials), 4 (design), and 7 (construction) were helpful in this regard
  Overdesign of bridge to account for perceived weaknesses of the method was discouraged
FHWA-HRT-11-026

## Slide 9: Stability Analysis Spreadsheet
LADOTD GRS Analysis Spreadsheet
Back and forth with Bridge Design section required iterative approach
  Span configuration
  Loads & moments
  Beam seat size
A spreadsheet was developed for the GRS design
  Quickly accommodated minor changes in structural design
  Allowed for parametric studies to get a feel for sensitivity of the design to various factors

## Slide 10: Stability Analysis Spreadsheet

## Slide 11: Specifications & Bids

## Slide 12: Specifications
FHWA guide spec was finalized in August 2012
  Unfortunately, we began writing our spec in June 2012
LADOTD spec was based on:
  Our existing MSE wall spec
  FHWA Implementation Guide
  Other states’ GRS specs
Using the guide spec would have been MUCH easier
FHWA-HRT-12-051

## Slide 13: Specification Writing Challenges
Separating guidelines from necessary specifications
  This is difficult when you haven’t actually built one yet!
  Leave flexibility for a method type spec (i.e., backfill compaction)
Deciding what needs to go in the specification vs. plans
  This took several iterations based on FHWA and LADOTD feedback
  Leave flexibility for different facing elements
Writing for a specific audience
  Spec for a contractor is different than one written for in-house forces
  Allow District construction inspectors and engineers to review plans & specs
  In hindsight, the specification should have erred on the side of being more prescriptive
Addressing the availability of materials or new materials
  Approved products list?

## Slide 14: September 2013 Letting
Bids came back high
  DOTD Estimate: $1.9M
  High Bidder: $3.5M
  Low Bidder: $3.0M
Contractor comments:
  Unfamiliar type of work
  Solid blocks & stained blocks too costly/difficult to obtain
  75-day project duration too tight
  Stone backfill in spec was not readily obtainable
  Wingwall details unclear
Plans & specs were modified based on contractor feedback
  Stained blocks removed
  Hollow blocks added
  Project duration increased to 90 days
  Backfill specs changed
  Additional wingwall details added to plans
  Scheduled mandatory pre-bid meeting with FHWA expert
Intent was to decrease unit cost of GRS pay item

## Slide 15: Aggregate Gradation Specification
LADOTD Standard Spec book has Grades A-F for stone
  All gradations were compared to AASHTO 89 stone
  Grade F matched AASHTO 89 very closely
  Grade F was selected for 1st spec
Contractors were not familiar with Grade F stone
  For reletting, a Grade A stone was specified (similar to #57)
Chart: Backfill Aggregate Gradations
| 38 | 25 | 19 | 13 | 10 | 5 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
AASHTO 89 (min) | 100 | 100 | 100 | 100 | 90 | 20 | 5 | #N/A | 0 | 0 | 0 | 0 | 0 | 0
Grade A (min) | 100 | 90 | #N/A | 25 | #N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grade F (min) | 100 | 100 | 100 | 90 | #N/A | 15 | 0 | #N/A | 0 | 0 | 0 | 0 | 0 | 0
AASHTO 89 (max) | 100 | 100 | 100 | 100 | 100 | 55 | 30 | #N/A | 10 | #N/A | #N/A | 5 | #N/A | #N/A
Grade A (max) | 100 | 100 | #N/A | 60 | #N/A | 10 | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1
Grade F (max) | 100 | 100 | 100 | 100 | #N/A | 60 | 15 | #N/A | 5 | #N/A | #N/A | #N/A | #N/A | 1

## Slide 16: CMU Block Specification
Tried to reduce block spec from 4,000 psi to 1,900 psi (ASTM C 90)
  4,000 psi may not be critical in a non-shrink swell environment
Local FHWA office rejected the spec change, because
  FHWA Implementation Guide recommends 4,000 psi
  Quote from semi-local supplier suggested no cost difference between 4,000 psi and 1,900 psi blocks
Hollow CMU Blocks

## Slide 17: March 2014 ReLetting
Bids still came back high
  DOTD Estimate: $2.2M (116%)
    Increase partially due to correcting a mistake in the GRS unit cost estimate
  High Bidder: $4.0M (114%)
  Low Bidder: $3.1M (103%)
Low bidder’s unit cost for GRS was $150/sf for both bids
  Difference of 4 to 5 times LADOTD estimate
  Even after addressing Contractor feedback, no change
Only traditional bridge (i.e., pile driving) contractors bid on the project
  Were bids intentionally high?
  Would earthwork contractors have been more competitive?
First comment at pre-bid meeting “Can we VE driven piles instead?”
  No technical questions were asked (as usual)
Project was awarded to low bidder in spite of high bids

## Slide 18: Construction

## Slide 19: Cofferdam
Although channel was mostly static, too deep for earthen dams
  Cofferdam was required
Permit stipulated that canal could not be fully blocked
  Separate cofferdams for each side of abutment
Cofferdam Estimate
  Low Bidder: $65K
  High Bidder: $365K
Building RSF Inside Cofferdam

## Slide 20: Cofferdam
Was there confusion among contractors as to the best dewatering strategy?
Low bidder claimed permit wasn’t available for review early enough
Cofferdams impacted construction schedule
  Did the low bidder underestimate the dewatering requirements for the project?
Compacting Lift Inside Cofferdam

## Slide 21: CMU Block Alignment
First abutment had block alignment problems
  Tilting out of plumb
  Sliding away from abutment during compaction
Contractor’s request to grind blocks & use shims was initially rejected
We first ruled out
  First row - was placed carefully & surveyed
  Block tolerances - were OK
Constructing First Row

## Slide 22: CMU Block Alignment
Method spec did not force adherence to good practices from the Implementation Guide
  Hand tamping
  Walking on top of blocks
LADOTD Recommendations
  Improve compaction methods
  Grind & shim only when needed
Improved compaction methods fixed most problems
  Using solid blocks on the 2nd bridge reduced sliding
  Flexibility for field engineer to modify method spec helped to achieve a better product
Compacting Against CMU Blocks

## Slide 23: CMU Block Integrity
Block supplier provided certs at beginning of project
  Showed passing block strength
Blocks delivered to site showed damage
  Some were cracked on pallet
  Others cracked during construction
Spec only required certs, no regimented QA/QC plan
  Local FHWA office requested independent testing after visiting site
Hollow CMU Compressive Strength Cert.

## Slide 24: CMU Block Integrity
Date | Block | Compressive Strength (psi) |  | 
Tested | Type | Tested | Required | Ratio
Aug-15 | Hollow | 1490 | 4000 | 37%
 | Solid | 2370 | 4000 | 59%
Sep-15 | Hollow | 1650 | 4000 | 41%
 | Solid | 3110 | 4000 | 78%
Nov-15 | Hollow | 2670 | 4000 | 67%
 | Hollow | 2600 | 4000 | 65%
 | Hollow * | 2817 | 4000 | 70%
 | Solid * | 4492 | 4000 | 112%
LTRC tested hollow and solid blocks in Aug & Sept 2015
  All blocks < 4,000 psi
  Hollow blocks < 1,900 psi
  Contractor did not furnish results
Contractor: spec was confusing
  Required 4,000 psi strength in addition to ASTM C 90
  Thus, 1,900 psi should be used
LTRC and Contractor’s lab tested again in Nov 2015
  Hollow blocks < 4,000 psi
  Solid blocks passed
CMU Compressive Strength Test Results
* Contractor’s Independent Lab

## Slide 25: CMU Block Integrity
Cracked Blocks Delivered to Site
Lack of transparency from Contractor led to 1st bridge being completed before issue could be resolved
  Contractor’s pay will be penalized
  Contractor must grout all cracked hollow blocks
Hollow blocks were rejected for 2nd bridge
  Contractor was allowed to use solid blocks at no added cost

## Slide 26: Bearing Bed Reinforcement
Contractor forgot to install bearing bed reinforcing
  “Can we just leave this out?”
Had to cut geosynthetic to avoid deconstructing the abutment completely
  Seams were staggered vertically
Clearly a case of field personnel not reading the Implementation Guide or plans
  Yes, the Contractor asked for extra time as a result!
GRS Profile Detail – Bearing Bed Reinforcing

## Slide 27: Approach Construction
Contractor tore out approaches early in project
  Brought in wet material which delayed subgrade prep
  GRS schedule affected due to concurrent approach work
  Delays spread to all phases of the project
Contractor submitted several claims for extra time
  YouTube video from the pre-bid meeting was “misleading”
Looking South Along Hwy 91 from Cofferdam

## Slide 28: Lessons Learned (DESIGN)
Follow the Implementation Guide
Use a spreadsheet to get a handle on the sensitivity of the GRS abutment to changes in various design parameters
Help educate the Department about the project
  Discourage overdesign just because it’s a “new” technology
  Provide Implementation Guide to Bridge Engineers & Project Managers
  We are considering additional GRS implementation as a result of success in this regard

## Slide 29: Lessons Learned (Specifications)
Use the FHWA guide spec as much as possible!
Let experienced district/field personnel review plans & specs
Separate specs from guidelines, plans versus specs
  Leave flexibility for experienced field personnel to enforce/modify method compaction spec if needed
Make spec relevant locally
  Climate concerns
  Material availability
Make sure local FHWA reps are in touch with FHWA subject matter experts

## Slide 30: Lessons Learned (Bids)
Hold a mandatory pre-bid meeting
Inform potential bidders that a YouTube video is not the basis for a bid
Make earthwork contractors aware of the project letting

## Slide 31: Lessons Learned (Construction)
For pilot project, select a site that is easy to dewater
Enforce compaction spec
  Require certain best practices such as hand tamping and walking on blocks – referring to Implementation Guide is not enough
  Since a method spec is harder to quantify with records, make sure the inspector is experienced
  Discourage modifications to the blocks as substitute for good compaction
Incorporate a detailed QA/QC plan for the facing elements
  Have a mechanism to reject facing elements in the field
Review plans and specs with contractor on a regular basis